## Project Tracker
Multi-Project Overview & Budget Tracker
AI Virtual Assistant & Executive Administrative Support System
Project ID | Project Name | Client Name | Start Date | Target End Date | Budget ($) | Actual Spend ($) | % Complete | Health Status
PRJ-401 | Executive CRM Overhaul | Vanguard Capital | 2026-07-01 | 2026-08-15 | 15000 | 8500 | 65% | On Track
PRJ-402 | Inbox Zero Automation Suite | Acme Corp | 2026-07-10 | 2026-07-31 | 6000 | 4200 | 80% | On Track
PRJ-403 | SOP Manual & Doc Creation | Nexus Global | 2026-07-15 | 2026-08-10 | 8000 | 3000 | 40% | On Track
PRJ-404 | Q3 Executive Slide Deck Design | Horizon Health | 2026-07-18 | 2026-07-25 | 3500 | 2800 | 90% | On Track
PRJ-405 | E-Commerce Logistics Audit | Apex Retailers | 2026-07-05 | 2026-08-05 | 10000 | 9500 | 50% | Pending